## Project Timelines 2021
PHASE |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION
PROJECT | Booked Revenue |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  |  | 2021-11-01 |  |  |  | 2021-12-01
|  | 7/12 - 7/17 | 7/19 - 7/24 | 7/26 - 7/31 | 8/2 - 8/7 | 8/9 - 8/14 | 8/16 - 8/21 | 8/23 - 8/28 | 8/30 - 9/4 | 9/6 - 9/11 | 9/13 - 9/19 | 9/20 - 9/25 | 9/27 - 10/2 | 10/4 - 10/9 | 10/11 - 10/16 | 10/18 - 10/23 | 10/25 - 10/30 | 11/1 - 11/6 | 11/8 - 11/13 | 11/15 - 11/20 | 11/22 - 11/27 | 11/29 - 12/4 | 12/6 - 12/11 | 12/13 - 12/18 | 12/20 - 12/25 | 12/27 - 1/1
CLIENT NAME | BOOKED | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
CLIENT NAME | BOOKED |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 94 |  | 8 | 10 | 5 | 4 | 10 | 10 | 10 | 12 | 7 | 8 | 10 | 12
CLIENT NAME | BOOKED | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 57 | [5 empty] | 7 | 9 | 10 | 10 | 6 | 5 | 10 | 9 | 8 | 10 | 11 | 10
TOTAL HOURS PER WEEK |  | 10 | 18 | 20 | 15 | 14 | 27 | 29 | 30 | 32 | 23 | 23 | 30 | 21 | 8 | 10 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Project Timelines 2022
PHASE |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION | [17 empty] | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION
PROJECT | Booked Revenue | Janurary 2022 |  |  |  | 2022-02-01 |  |  |  | 2022-03-01 |  |  |  |  | 2022-04-01 |  |  |  | 2022-05-01 |  |  |  | 2020-06-01 |  |  |  | 2020-07-01 |  |  |  |  | 2020-08-01 |  |  |  | 2020-09-01 |  |  |  | 2020-10-01 |  |  |  |  | 2020-11-01 |  |  |  | 2020-12-01 |  |  |  | Janurary 2021 |  |  |  |  | 2021-02-01 |  |  |  | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  |  | 2021-08-01 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  |  | 2021-11-01 |  |  |  | 2021-12-01
|  | 1/2-1/7 | 1/9-14 | 1/20 - 1/25 | 1/27 - 2/1 | 2/3 - 2/8 | 2/10 - 2/15 | 2/17 - 2/22 | 2/24 - 2/29 | 3/2 - 2/7 | 3/9 - 3/14 | 3/16 - 3/21 | 3/23 - 3/28 | 3/30 - 4/4 | 4/6 - 4/11 | 4/13 -1/18 | 4/20 - 4/25 | 4/27 - 5/2 | 5/4 - 5/9 | 5/11 - 5/16 | 5/18 - 5/23 | 5/25 - 5/30 | 6/1 - 6/6 | 6/8 - 6/13 | 6/15 - 6/20 | 6/22 - 6/27 | 6/29 - 7/4 | 7/6 - 7/11 | 7/13 - 7/18 | 7/20 - 7/25 | 7/27 - 8/1 | 8/3 - 8/8 | 8/10 - 8/15 | 8/17 - 8/22 | 8/24 - 8/29 | 8/31 - 9/5 | 9/7 - 9/12 | 9/14 - 9/19 | 9/21 - 9/26 | 9/28 - 10/3 | 10/5 - 10/10 | 10/12 - 10/17 | 1/19 - 10/24 | 10/26 - 10/31 | 11/2 - 11/7 | 11/9 - 11/14 | 11/16 - 11/21 | 11/23 - 11/28 | 11/30 - 12/5 | 12/7 - 12/12 | 12/14 - 12/19 | 12/21 - 12/26 | 12/28 - 1/2 | 1/4 - 1/9 | 1/11 - 1/16 | 1/18 - 1/23 | 1/25 - 1/30 | 2/1 - 2/6 | 2/8 - 2/13 | 2/15 - 2/20 | 2/22 - 2/27 | 3/1 - 3/6 | 3/8 - 3/13 | 3/15 - 3/20 | 3/22- 3/27 | 3/29 - 4/3 | 4/5 - 4/10 | 4/12 - 4/17 | 4/19 - 4/24 | 4/26 - 5/1 | 5/3 - 5/8 | 5/10 - 5/15 | 5/17 - 5/22 | 5/24 - 5/29 | 5/31 - 6-5 | 6/7 - 6/12 | 6/14 - 6/19 | 6/21 - 6/26 | 6/28 - 7/3 | 7/5 - 7/10 | 7/12 - 7/17 | 7/19 - 7/24 | 7/26 - 7/31 | 8/2 - 8/7 | 8/9 - 8/14 | 8/16 - 8/21 | 8/23 - 8/28 | 8/30 - 9/4 | 9/6 - 9/11 | 9/13 - 9/19 | 9/20 - 9/25 | 9/27 - 10/2 | 10/4 - 10/9 | 10/11 - 10/16 | 10/18 - 10/23 | 10/25 - 10/30 | 11/1 - 11/6 | 11/8 - 11/13 | 11/15 - 11/20 | 11/22 - 11/27 | 11/29 - 12/4 | 12/6 - 12/11 | 12/13 - 12/18 | 12/20 - 12/25 | 12/27 - 1/1
CLIENT NAME | BOOKED | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [13 empty] | CLIENT NAME | BOOKED | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [13 empty] | CLIENT NAME | BOOKED | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [13 empty] | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
CLIENT HOURS | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [13 empty] | CLIENT HOURS | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [13 empty] | CLIENT HOURS | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
CLIENT NAME | BOOKED |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [12 empty] | CLIENT NAME | BOOKED |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [12 empty] | CLIENT NAME | BOOKED |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 94 |  | 8 | 10 | 5 | 4 | 10 | 10 | 10 | 12 | 7 | 8 | 10 | 12 | [12 empty] | CLIENT HOURS | 94 |  | 8 | 10 | 5 | 4 | 10 | 10 | 10 | 12 | 7 | 8 | 10 | 12 | [12 empty] | CLIENT HOURS | 94 |  | 8 | 10 | 5 | 4 | 10 | 10 | 10 | 12 | 7 | 8 | 10 | 12
CLIENT NAME | BOOKED | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [8 empty] | CLIENT NAME | BOOKED | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | [8 empty] | CLIENT NAME | BOOKED | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 57 | [5 empty] | 7 | 9 | 10 | 10 | 6 | 5 | 10 | 9 | 8 | 10 | 11 | 10 | [8 empty] | CLIENT HOURS | 57 | [5 empty] | 7 | 9 | 10 | 10 | 6 | 5 | 10 | 9 | 8 | 10 | 11 | 10 | [8 empty] | CLIENT HOURS | 57 | [5 empty] | 7 | 9 | 10 | 10 | 6 | 5 | 10 | 9 | 8 | 10 | 11 | 10
TOTAL HOURS PER WEEK |  | 10 | 18 | 20 | 15 | 14 | 27 | 29 | 30 | 32 | 23 | 23 | 30 | 21 | 8 | 10 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TOTAL HOURS PER WEEK |  | 10 | 18 | 20 | 15 | 14 | 27 | 29 | 30 | 32 | 23 | 23 | 30 | 21 | 8 | 10 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | TOTAL HOURS PER WEEK |  | 10 | 18 | 20 | 15 | 14 | 27 | 29 | 30 | 32 | 23 | 23 | 30 | 21 | 8 | 10 | 11 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## LOST-Timelines
PHASE |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION |  |  | AGREEMENT | CONCEPTUAL DESIGN | SHOPPING | DETAILED DESIGN | FINAL PLANS | CONSTRUCTION
PROJECT | Booked Revenue |  | 2021-06-01 |  |  |  | 2021-07-01 |  |  |  |  | Auguest 2021 |  |  |  | 2021-09-01 |  |  |  | 2021-10-01 |  |  |  |  | 2021-11-01 |  |  |  | 2021-12-01
|  | 5/24 - 5/29 | 5/31 - 6-5 | 6/7 - 6/12 | 6/14 - 6/19 | 6/21 - 6/26 | 6/28 - 7/3 | 7/5 - 7/10 | 7/12 - 7/17 | 7/19 - 7/24 | 7/26 - 7/31 | 8/2 - 8/7 | 8/9 - 8/14 | 8/16 - 8/21 | 8/23 - 8/28 | 8/30 - 9/4 | 9/6 - 9/11 | 9/13 - 9/19 | 9/20 - 9/25 | 9/27 - 10/2 | 10/4 - 10/9 | 10/11 - 10/16 | 10/18 - 10/23 | 10/25 - 10/30 | 11/1 - 11/6 | 11/8 - 11/13 | 11/15 - 11/20 | 11/22 - 11/27 | 11/29 - 12/4 | 12/6 - 12/11 | 12/13 - 12/18 | 12/20 - 12/25 | 12/27 - 1/1
CLIENT NAME | BOOKED | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 120 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
CLIENT NAME | BOOKED |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 94 |  | 8 | 10 | 5 | 4 | 10 | 10 | 10 | 12 | 7 | 8 | 10 | 12
CLIENT NAME | BOOKED | [5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
CLIENT HOURS | 57 | [5 empty] | 7 | 9 | 10 | 10 | 6 | 5 | 10 | 9 | 8 | 10 | 11 | 10

## Domini (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 490.25 | 2020-10-13 | 1.5 | 55.5 | 2020-09-11 | Designer Pay |  | 490.25 | 2020-10-13 | Initial Fee | #01354 | 730 | READY FOR PICKUP
Total Income | 2348.75 | 2020-10-15 | 1 | 37 |  |  |  |  | 2020-12-22 | Design Fee | #01376 | 1618.75 | READY FOR INSTALL
Total Profit | 1858.5 | 2020-10-15 | 3.25 | 120.25 | [8 empty] | INSTALLED
Profit % | 79.13% | 2020-10-16 | 1.5 | 55.5 | [8 empty] | AWATING RE-DELIVERY
Total Contracted Hours | 16 | 2020-10-17 | 2.25 | 83.25
Total Hours Used | 13.25 | 2020-12-07 | 1.25 | 46.25
Hours Remaining | 2.75 | 2020-12-10 | 2.5 | 92.5
0
0
Design Hours | 4.1714 |  |  | 0
9.25 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Mahoney (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 2053.5 | 2020-09-30 | 4.5 | 166.5 | 2020-09-11 | Designer Pay |  | 2053.5 | 2020-09-30 | Initial Design Fee | n/a | 4000 | READY FOR PICKUP
Total Income | 12266 | 2020-10-06 | 2 | 74 |  |  |  |  | 2020-11-24 | Design Time | #01367 | 4575 | READY FOR INSTALL
Total Profit | 10212.5 | 2020-10-07 | 2 | 74 |  |  |  |  | 2020-12-22 | Weekly Draw 2 | #01379 | 2500 | INSTALLED
Profit % | 83.26% | 2020-10-07 | 1 | 37 |  |  |  |  | 2021-12-30 |  |  | 1191 | AWATING RE-DELIVERY
Total Contracted Hours | 112 | 2020-10-12 | 2 | 74
Total Hours Used | 55.5 | 2020-10-13 | 4 | 148 | [5 empty] | *activated weekly draw 1/1
Hours Remaining | 56.5 | 2020-10-19 | 3.5 | 129.5
|  | 2020-10-20 | 1 | 37
Hours Billed for | 70.0914 | 2020-10-20 | 2 | 74
Weekly Draw Hours | 6.8 | 2020-10-20 | 1 | 37
|  | 2020-10-26 | 5.5 | 203.5
|  | 2020-10-30 | 1 | 37
|  | 2020-11-03 | 6 | 222
|  | 2020-11-04 | 1 | 37
|  | 2020-11-06 | 1.5 | 55.5
|  | 2020-11-09 | 2.5 | 92.5
|  | 2020-11-11 | 1 | 37
|  | 2020-11-14 | 2 | 74
|  | 2020-11-16 | 1 | 37
|  | 2020-11-17 | 1 | 37
|  | 2020-11-19 | 1 | 37
|  | 2020-11-20 | 2.5 | 92.5
|  | 2020-12-01 | 1 | 37
|  | 2020-12-03 | 1 | 37
|  | 2020-12-04 | 2 | 74
|  | 2020-12-08 | 2.5 | 92.5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Soper (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 1211.75 | 2020-11-28 | 2.25 | 83.25 | 2020-09-11 | Designer Pay |  | 1211.75 | 2020-10-28 | Initial Fee | #01357 | 4294 | READY FOR PICKUP
Total Income | 5659 | 2020-11-05 | 2 | 74 |  |  |  |  | 2020-12-22 | Weekly Draw 5 | #01380 | 1365 | READY FOR INSTALL
Total Profit | 4447.25 | 2020-11-17 | 1 | 37 | [5 empty] | Weekly Draw 6 |  |  | INSTALLED
Profit % | 78.59% | 2020-11-17 | 1.5 | 55.5 | [5 empty] | Weekly Draw 7 |  |  | AWATING RE-DELIVERY
Total Contracted Hours | 140 | 2020-12-01 | 3.25 | 120.25 | [5 empty] | Weekly Draw 8
Total Hours Used | 32.75 | 2020-12-01 | 4.5 | 166.5 | [5 empty] | Weekly Draw 9
Hours Remaining | 107.25 | 2020-12-07 | 5 | 185 | [5 empty] | Weekly Draw 10
|  | 2020-12-08 | 4.5 | 166.5 | [5 empty] | Weekly Draw 11
|  | 2020-12-09 | 2 | 74 | [5 empty] | Weekly Draw 12
Hours Paid | 32.3371 | 2020-12-09 | 2 | 74 | [5 empty] | Weekly Draw 13
Difference on billing | 0.41286 | 2020-12-09 | 0.5 | 18.5 | [5 empty] | *activated weekly draw
|  | 2020-12-15 | 1.75 | 64.75
|  | 2020-12-15 | 2 | 74
|  | 2021-03-04 | 0.5 | 18.5
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Walsh (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 1036 | 2020-10-16 | 2.5 | 92.5 | 2020-09-11 | Designer Pay |  | 1036 | 2020-10-16 | Initial Fee | #01338 | 1575 | READY FOR PICKUP
Total Income | 4156.25 | 2020-10-20 | 2.75 | 101.75 |  |  |  |  | 2020-12-22 | Design Invoice | #01381 | 2581.25 | READY FOR INSTALL
Total Profit | 3120.25 | 2020-10-21 | 2 | 74 | [8 empty] | INSTALLED
Profit % | 75.07% | 2020-10-22 | 2 | 74 | [8 empty] | AWATING RE-DELIVERY
Total Contracted Hours | 75 | 2020-11-02 | 2.5 | 92.5
Total Hours Used | 28 | 2020-11-05 | 2.5 | 92.5
Hours Remaining | 47 | 2020-11-09 | 3 | 111
|  | 2020-11-11 | 3 | 111
|  | 2020-11-12 | 2 | 74
|  | 2020-11-18 | 1.5 | 55.5
|  | 2020-12-30 | 2.25 | 83.25
|  | 2021-01-14 | 2 | 74
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Gill-Tully (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 595.33 | 2021-11-23 | 3.5 | 129.5 |  | Designer Pay |  | 595.33 |  |  |  | 1453 | READY FOR PICKUP
Total Income | 7265 | 2021-12-28 | 1.5 | 55.5 | [7 empty] | 1453 | READY FOR INSTALL
Total Profit | 6669.67 | 2021-01-05 | 2.96 | 109.52 | [7 empty] | 1453 | INSTALLED
Profit % | 91.81% | 2021-01-20 | 2.5 | 92.5 | [7 empty] | 1453 | AWATING RE-DELIVERY
Total Contracted Hours | 51 | 2021-01-25 | 2.75 | 101.75 | [7 empty] | 1453
Total Hours Used | 22.45 | 2021-01-28 | 2.88 | 106.56
Hours Remaining | 28.55 | 2021-02-01 | 1.5 | 55.5
|  | 2021-02-08 | 1.45 | 53.65
|  | 2021-02-11 | 1.75 | 64.75
Hours billed for | 41.5143 | 2021-02-15 | 1.66 | 61.42
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Ahmed (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 0 |  |  | 0 |  | Designer Pay |  | 0 |  |  |  |  | READY FOR PICKUP
Total Income | 0 |  |  | 0 | [8 empty] | READY FOR INSTALL
Total Profit | 0 |  |  | 0 | [8 empty] | INSTALLED
Profit % | #DIV/0! |  |  | 0 | [8 empty] | AWATING RE-DELIVERY
Total Contracted Hours | 51 |  |  | 0
Total Hours Used | 0 |  |  | 0
Hours Remaining | 51 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Poppe (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 0 |  |  | 0 |  | Designer Pay |  | 0 |  |  |  |  | READY FOR PICKUP
Total Income | 0 |  |  | 0 |  |  |  | 0 |  |  |  |  | READY FOR INSTALL
Total Profit | 0 |  |  | 0 | [8 empty] | INSTALLED
Profit % | #DIV/0! |  |  | 0 | [8 empty] | AWATING RE-DELIVERY
Total Contracted Hours | 51 |  |  | 0
Total Hours Used | 0 |  |  | 0
Hours Remaining | 51 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Delia and Tim Kiely - PHR (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 2483.07 | 2020-08-31 | 67.11 | 2483.07 | 2020-09-11 | Designer Pay |  | 2483.07 | 2019-12-11 | Design Time | Invoice 01285 | 4795 | READY FOR PICKUP
Total Income | 8842.25 |  |  | 0 |  | Designer Pay |  | 0 | 2020-03-13 | Design Time | Invoice 01295 | 1951.5 | READY FOR INSTALL
Total Profit | 6359.18 |  |  | 0 |  |  |  |  | 2020-04-02 | Design Time | Invoice 01307 | 270.25 | INSTALLED
Profit % | 71.92% |  |  | 0 |  |  |  |  | 2020-06-26 | Design Time | Invoice 01317 | 1614.25 | AWATING RE-DELIVERY
Total Contracted Hours | 87 |  |  | 0 |  |  |  |  | 2020-09-08 | Design Time | Invoice 01347 | 211.25
Total Hours Used | 67.11 |  |  | 0
Hours Remaining | 19.89 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Lyons - PHR (hidden)
TOTAL PROFITABILITY |  | BILLABLE HOURS TRACKING |  |  | ALL JOB EXPENSES |  |  |  | ALL JOB INCOME |  |  |  | SHIPPING TRACKING
|  | Date | Hours Worked | Cost of Hours | Date | EXPENSE ITEM | LINK TO PO | COST | Dates | INCOME ITEM | LINK TO INVOICES | AMOUNT | SHIPPING STATUSES | CARRIER | Pick Up Location or Direct Ship | Order Date | Quantity | Item | Vendor | Room Location | Estimated Ship Date | Notes:
Total Expenses | 0 |  |  | 0 | 2020-09-11 | Designer Pay |  | 0 | 2020-02-14 | Design Time | Invoice 01290 | 1493.5 | READY FOR PICKUP
Total Income | 10457.75 |  |  | 0 |  |  |  |  | 2019-03-14 | Design Time | Invoice 01216 | 1227.5 | READY FOR INSTALL
Total Profit | 10457.75 |  |  | 0 |  |  |  |  | 2019-08-18 | Design Time | Invoice 01253 | 1843.75 | INSTALLED
Profit % | 100% |  |  | 0 | [8 empty] | AWATING RE-DELIVERY
Total Contracted Hours | 100 |  |  | 0
Total Hours Used | 0 |  |  | 0
Hours Remaining | 100 |  |  | 0
0
|  |  |  | 0 |  |  |  |  | Billed to Client
|  |  |  | 0 |  |  |  |  | 2020-02-14 | Desgin Time | Invoice 01279 | 1772.5
|  |  |  | 0 |  |  |  |  | 2020-04-16 | Design Time | Invoice 01309 | 1641
|  |  |  | 0 |  |  |  |  | 2020-06-26 | Design Time | Invoice 01319 | 1662
|  |  |  | 0 |  |  |  |  | 2020-09-08 | Design Time | Invoice 01342 | 817.5
0
0
|  |  |  | 0 |  |  |  |  | **need to track hours for client
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Fedele (hidden)
CLIENT DROPBOX FOLDER - Click here for receipts and other job related documents
Material / Labor Type | Cost Per Unit | Unit Quantity | Material / Labor Costs | Actual Costs | LABOR COST TRACKING | [7 empty] | Job Audit Tracking
wall stud 8' | 2.7 | 0 | 0 |  | Time Sheets | Week of: 5/25/20 | [7 empty] | Proposed | Current | Completed
wall stud 12' | 4.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Material Costs | 0 | 0
green stud 8' | 4.88 | 0 | 0 |  | Davon | 18.25 | 328.5 |  |  | 8.25 | 8 | 2 | Labor Costs | 2895 | 1523.5
collar tie (2x8x10 douglas fir) | 14.69 | 0 | 0 |  | Cary | 17.5 | 315 |  |  | 8 | 7.5 | 2 | Total Costs | 2895 | 1523.5
drywall | 7.86 | 0 | 0 |  | Justin | 16.5 | 297 |  |  | 7.75 | 6.75 | 2 | Total Income | 3763.5 | 3763.5
basement board | 8.49 | 0 | 0 |  | TOTAL | 35.75 | 643.5 | [5 empty] | Profit | 868.5 | 2240
green board | 10.98 | 0 | 0 |  | Time Sheets | Week of: | [6 empty] | Date Contract Signed:
shiplap for walls 6.16 sq. ft. | 29.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Project Start Date:
door casing 7' (white colonial) | 6.65 | 0 | 0 |  | Davon | 0 | 0 | [5 empty] | Project Completion Date:
baseboard 16' (white colonial) | 16.99 | 0 | 0 |  | Cary | 0 | 0 | [5 empty] | Down Payment Amount: |  | 1881 | 2020-05-28
base shoe 12' (prefinished white) | 3.28 | 0 | 0 |  | Justin | 0 | 0 | [5 empty] | Draw 1 Amount:
Golden Oak colonial base 12' | 25.49 | 0 | 0 |  | TOTAL | 0 | 0 | [5 empty] | Draw 2 Amount:
Golden Oak base shoe 12' | 29.99 | 0 | 0 |  | Time Sheets | Week of: | [6 empty] | Draw 3 Amount:
Golden Oak door casing | 21.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Draw 4 Amount:
wall insulation R15 kraft faced 67.8 sq. ft. | 37.98 | 0 | 0 |  | Davon | 0 | 0 | [5 empty] | Final Payment Amount: |  | 1882.5 | 2020-06-03
ceiling insulation R19 kraft faced 75.1 sq. ft. | 29.99 | 0 | 0 |  | Jessica | 0 | 0 | [5 empty] | NOTES
single panel pre-hung door 36" (white) | 189 | 0 | 0 |  | Cary | 0 | 0 | [5 empty] | WHAT WENT WELL?
single panel pre-hung door 24" x 66" tall (white) | 195 | 0 | 0 |  | Justin | 0 | 0
single panel slab door 36" x 66" tall (white) | 225 | 0 | 0 |  | TOTAL | 0 | 0
single panel slab door 30" x 66" tall (white) | 216 | 0 | 0 |  | Time Sheets | Week of:
single panel slab door 42" (white) | 375 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
single glass panel slab door 32" (white) | 185 | 0 | 0 |  | Davon | 0 | 0
6 panel pre-hung door 30" (white) | 104.99 | 0 | 0 |  | Jessica | 0 | 0
6 panel door slab 30" (white) | 75.99 | 0 | 0 |  | Cary | 0 | 0
6 panel pre-hung door 30" (golden oak) | 208.99 | 0 | 0 |  | Justin | 0 | 0
6 panel slab door 36" (golden oak) | 160.99 | 0 | 0 |  | TOTAL | 0 | 0
barn style door track | 89.99 | 0 | 0 |  | Time Sheets | Week of:
half door barn style 32" | 150 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
36" bifold door | 80 | 0 | 0 |  | Davon | 0 | 0
Jeld-Wen replacement vinyl window | 145 | 0 | 0 |  | Jessica | 0 | 0
1x8x12' white shelving | 8.17 | 0 | 0 |  | Cary | 0 | 0
bi-pass door jam 1 x 6 x 8' | 3.92 | 0 | 0 |  | Justin | 0 | 0
dricore subfloor | 6.25 | 0 | 0 |  | TOTAL | 0 | 0
laminate floor - gray 20.15 sq. ft. | 47.49 | 0 | 0 |  | Time Sheets | Week of: | [6 empty] | WHAT DID NOT GO WELL?
tile backer 32x60x1/2 | 9.98 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
tile backer 4x4x1/4 | 9.69 | 0 | 0 |  | Davon | 0 | 0
tile mortar, grout, sealer | 80 | 0 | 0 |  | Jessica | 0 | 0
12 x 12 gray tile - Braswell Haze | 1.75 | 0 | 0 |  | Cary | 0 | 0
kitchen faucet | 129.99 | 0 | 0 |  | Justin | 0 | 0
bathroom faucet | 89.99 | 0 | 0 |  | TOTAL | 0 | 0
shower & tub faucet | 184.99 | 0 | 0 |  | Time Sheets | Week of:
bathroom fixtures | 75 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
tub and surround | 598 | 0 | 0 |  | Davon | 0 | 0
Sterling Finese Shower Door | 279 | 0 | 0 |  | Jessica | 0 | 0
vanity | 750 | 0 | 0 |  | Cary | 0 | 0
mirror | 100 | 0 | 0 |  | Justin | 0 | 0
vanity lights | 100 | 0 | 0 |  | TOTAL | 0 | 0
toilet | 300 | 0 | 0 |  | Time Sheets | Week of:
exhaust fan and venting | 250 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
wood for built in bookcase | 250 | 0 | 0 |  | Davon | 0 | 0
cabinets white shaker style | 515.62 | 0 | 0 |  | Jessica | 0 | 0
counter top - quartz | 750 | 0 | 0 |  | Cary | 0 | 0
solatube w/ light and fan | 1000 | 0 | 0 |  | Justin | 0 | 0
lumber for shoring roof joists | 200 | 0 | 0 |  | TOTAL | 0 | 0
materials for crawlspace hatch | 500 | 0 | 0 |  | Time Sheets | Week of:
shelves 1x24x36 edge glued pine | 16.69 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
laminate counter top $20/ft | 20 | 0 | 0 |  | Davon | 0 | 0
paint | 30 | 0 | 0 |  | Jessica | 0 | 0
Total Material Cost |  |  | 0 |  | Cary | 0 | 0
Plus Tax |  |  | 0 | 0 | Justin | 0 | 0
plumber |  |  | 0 |  | TOTAL | 0 | 0
electrician |  |  | 0 |  | Time Sheets | Week of:
HVAC |  |  | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Egress Window |  |  | 0 |  | Davon | 0 | 0
drywaller |  |  | 0 |  | Jessica | 0 | 0
painter |  |  | 0 |  | Cary | 0 | 0
insulation |  |  | 0 |  | Justin | 0 | 0
carpet installation |  |  | 0 |  | TOTAL | 0 | 0
Dumpster |  |  | 1020 | 880 | Time Sheets | Week of:
Glass Block Windows |  |  | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Skylight |  |  | 0 |  | Davon | 0 | 0
Drop Ceiling |  |  | 0 |  | Jessica | 0 | 0
Permit |  |  | 0 |  | Cary | 0 | 0
Photographer |  |  | 0 |  | Justin | 0 | 0
Edible Arrangement |  |  | 0 |  | TOTAL | 0 | 0
Back to Basics Employee Labor ($800/day) | 625 | 3 | 1875 | 643.5 | Time Sheets | Week of:
Total Labor Costs |  |  | 2895 | 1523.5 | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Total Variable Costs |  |  | 2895 | 1523.5 | Davon | 0 | 0
Profit (30%) |  |  | 868.5 |  | Jessica | 0 | 0
Total Estimate |  |  | 3763.5 | 1523.5 | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0

## Roy (hidden)
CLIENT DROPBOX FOLDER - Click here for receipts and other job related documents
Material / Labor Type | Cost Per Unit | Unit Quantity | Material / Labor Costs | Actual Costs | LABOR COST TRACKING | [7 empty] | Job Audit Tracking
wall stud 8' | 2.7 | 0 | 0 |  | Time Sheets | Week of: 5/4/20 | [7 empty] | Proposed | Current | Completed
wall stud 12' | 4.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Material Costs | 0 | 0
green stud 8' | 4.88 | 0 | 0 |  | Davon | 1.5 | 27 |  |  |  | 1.5 |  | Labor Costs | 0 | 279
collar tie (2x8x10 douglas fir) | 14.69 | 0 | 0 |  | Cary | 1.5 | 27 |  |  |  | 1.5 |  | Total Costs | 0 | 279
drywall | 7.86 | 0 | 0 |  | Justin | 1.5 | 27 |  |  |  | 1.5 |  | Total Income | 0 | 400
basement board | 8.49 | 0 | 0 |  | TOTAL | 4.5 | 81 | [5 empty] | Profit | 0 | 121
green board | 10.98 | 0 | 0 |  | Time Sheets | Week of: 5/18/20 | [6 empty] | Date Contract Signed:
shiplap for walls 6.16 sq. ft. | 29.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Project Start Date:
door casing 7' (white colonial) | 6.65 | 0 | 0 |  | Davon | 3.25 | 58.5 |  |  | 1.25 |  | 2 | Project Completion Date:
baseboard 16' (white colonial) | 16.99 | 0 | 0 |  | Cary | 4.25 | 76.5 |  |  | 1.25 |  | 3 | Down Payment Amount: |  | 150 | 2020-05-08
base shoe 12' (prefinished white) | 3.28 | 0 | 0 |  | Justin | 3.5 | 63 |  |  | 1.25 |  | 2.25 | Change order #1 |  | 150 | 2020-05-22
Golden Oak colonial base 12' | 25.49 | 0 | 0 |  | TOTAL | 11 | 198 | [5 empty] | Change order #1 |  | 100 | 2020-05-28
Golden Oak base shoe 12' | 29.99 | 0 | 0 |  | Time Sheets | Week of: | [6 empty] | Draw 3 Amount:
Golden Oak door casing | 21.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Draw 4 Amount:
wall insulation R15 kraft faced 67.8 sq. ft. | 37.98 | 0 | 0 |  | Davon | 0 | 0 | [5 empty] | Final Payment Amount:
ceiling insulation R19 kraft faced 75.1 sq. ft. | 29.99 | 0 | 0 |  | Cary | 0 | 0 | [5 empty] | NOTES
single panel pre-hung door 36" (white) | 189 | 0 | 0 |  | Justin | 0 | 0 | [5 empty] | WHAT WENT WELL?
single panel pre-hung door 24" x 66" tall (white) | 195 | 0 | 0 |  | TOTAL | 0 | 0
single panel slab door 36" x 66" tall (white) | 225 | 0 | 0 |  | Time Sheets | Week of:
single panel slab door 30" x 66" tall (white) | 216 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
single panel slab door 42" (white) | 375 | 0 | 0 |  | Davon | 0 | 0
single glass panel slab door 32" (white) | 185 | 0 | 0 |  | Jessica | 0 | 0
6 panel pre-hung door 30" (white) | 104.99 | 0 | 0 |  | Cary | 0 | 0
6 panel door slab 30" (white) | 75.99 | 0 | 0 |  | Justin | 0 | 0
6 panel pre-hung door 30" (golden oak) | 208.99 | 0 | 0 |  | TOTAL | 0 | 0
6 panel slab door 36" (golden oak) | 160.99 | 0 | 0 |  | Time Sheets | Week of:
barn style door track | 89.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
half door barn style 32" | 150 | 0 | 0 |  | Davon | 0 | 0
36" bifold door | 80 | 0 | 0 |  | Jessica | 0 | 0
Jeld-Wen replacement vinyl window | 145 | 0 | 0 |  | Cary | 0 | 0
1x8x12' white shelving | 8.17 | 0 | 0 |  | Justin | 0 | 0
bi-pass door jam 1 x 6 x 8' | 3.92 | 0 | 0 |  | TOTAL | 0 | 0
dricore subfloor | 6.25 | 0 | 0 |  | Time Sheets | Week of:
laminate floor - gray 20.15 sq. ft. | 47.49 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | WHAT DID NOT GO WELL?
tile backer 32x60x1/2 | 9.98 | 0 | 0 |  | Davon | 0 | 0
tile backer 4x4x1/4 | 9.69 | 0 | 0 |  | Jessica | 0 | 0
tile mortar, grout, sealer | 80 | 0 | 0 |  | Cary | 0 | 0
12 x 12 gray tile - Braswell Haze | 1.75 | 0 | 0 |  | Justin | 0 | 0
kitchen faucet | 129.99 | 0 | 0 |  | TOTAL | 0 | 0
bathroom faucet | 89.99 | 0 | 0 |  | Time Sheets | Week of:
shower & tub faucet | 184.99 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
bathroom fixtures | 75 | 0 | 0 |  | Davon | 0 | 0
tub and surround | 598 | 0 | 0 |  | Jessica | 0 | 0
Sterling Finese Shower Door | 279 | 0 | 0 |  | Cary | 0 | 0
vanity | 750 | 0 | 0 |  | Justin | 0 | 0
mirror | 100 | 0 | 0 |  | TOTAL | 0 | 0
vanity lights | 100 | 0 | 0 |  | Time Sheets | Week of:
toilet | 300 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
exhaust fan and venting | 250 | 0 | 0 |  | Davon | 0 | 0
wood for built in bookcase | 250 | 0 | 0 |  | Jessica | 0 | 0
cabinets white shaker style | 515.62 | 0 | 0 |  | Cary | 0 | 0
counter top - quartz | 750 | 0 | 0 |  | Justin | 0 | 0
solatube w/ light and fan | 1000 | 0 | 0 |  | TOTAL | 0 | 0
lumber for shoring roof joists | 200 | 0 | 0 |  | Time Sheets | Week of:
materials for crawlspace hatch | 500 | 0 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
shelves 1x24x36 edge glued pine | 16.69 | 0 | 0 |  | Davon | 0 | 0
laminate counter top $20/ft | 20 | 0 | 0 |  | Jessica | 0 | 0
paint | 30 | 0 | 0 |  | Cary | 0 | 0
Total Material Cost |  |  | 0 |  | Justin | 0 | 0
Plus Tax |  |  | 0 | 0 | TOTAL | 0 | 0
plumber |  | 1 | 0 |  | Time Sheets | Week of:
electrician |  | 1 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
HVAC |  | 1 | 0 |  | Davon | 0 | 0
Egress Window |  | 1 | 0 |  | Jessica | 0 | 0
drywaller |  | 1 | 0 |  | Cary | 0 | 0
painter |  | 1 | 0 |  | Justin | 0 | 0
insulation |  | 1 | 0 |  | TOTAL | 0 | 0
carpet installation |  | 1 | 0 |  | Time Sheets | Week of:
Dumpster | 185 | 1 | 0 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Glass Block Windows |  | 1 | 0
Skylight |  | 1 | 0 |  | Davon | 0 | 0
Drop Ceiling |  | 1 | 0 |  | Jessica | 0 | 0
Permit | 150 | 0 | 0 |  | Cary | 0 | 0
Photographer | 100 | 1 | 0 |  | Justin | 0 | 0
Edible Arrangement | 100 | 1 | 0 |  | TOTAL | 0 | 0
Back to Basics Employee Labor ($800/day) | 800 | 0 | 0 | 279 | Time Sheets | Week of:
Total Labor Costs |  |  | 0 | 279 | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Total Variable Costs |  |  | 0 | 279 | Davon | 0 | 0
Profit (30%) |  |  | 0 |  | Jessica | 0 | 0
Total Estimate |  |  | 0 | 279 | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Davon | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Cary | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | TOTAL | 0 | 0

## Guise (hidden)
CLIENT DROPBOX FOLDER - Click here for receipts and other job related documents
Material / Labor Type | Cost Per Unit | Unit Quantity | Material / Labor Costs | Actual Costs | LABOR COST TRACKING | [7 empty] | Job Audit Tracking
wall stud 8' | 2.7 | 133 | 359.1 | 398.14 | Time Sheets | Week of: | [7 empty] | Proposed | Current | Completed
green stud 8' | 4.88 | 17 | 82.96 | 80.25 | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Material Costs | 10310.9107 | 0
door casing 7' (white colonial) | 6.65 | 7 | 46.55 |  | Tristan | 0 | 0 | [5 empty] | Labor Costs | 41350 | 14587.3
baseboard 16' (white colonial) | 16.99 | 11 | 186.89 |  | Jessica | 0 | 0 | [5 empty] | Total Costs | 51660.9107 | 14587.3
base shoe 12' (prefinished white) | 3.28 | 14 | 45.92 |  | Davon | 0 | 0 | [5 empty] | Total Income | 61993.0929 | 17504.76
wall insulation R15 kraft faced 67.8 sq. ft. | 37.98 | 16 | 607.68 |  | Jakob | 0 | 0 | [5 empty] | Profit | 10332.1821 | 2917.46
wall insulation R-11 unfaced 50 sq ft | 11.49 | 16 |  | 194
barn style door track | 89.99 | 2 | 179.98 |  | Justin | 0 | 0 | [5 empty] | Date Contract Signed:
barn style door | 159 | 2 | 318 |  | Carey | 0 | 0 | [5 empty] | Project Start Date:
1x8x12' white shelving | 8.17 | 6 | 49.02 |  | TOTAL | 0 | 0 | [5 empty] | Project Completion Date:
bi-pass door jam 1 x 6 x 8' | 3.92 | 3 | 11.76 |  | Time Sheets | Week of: | [6 empty] | Down Payment Amount:
luxury vinyl plank Armstrong River Falls silver oak (23.84 sq. ft.) | 30.75 | 29 | 891.75 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Down Payment Deposited Date:
luxury vinyl underlayment | 49.99 | 7 | 349.93 |  | Tristan | 0 | 0 | [5 empty] | Draw 1 Amount:
tile mortar, grout, sealer | 80 | 1 | 80 |  | Jessica | 0 | 0 | [5 empty] | Draw 1 Deposited Date:
12 x 12 gray tile - Braswell Haze | 1.75 | 45 | 78.75 |  | Davon | 0 | 0 | [5 empty] | Draw 2 Amount:
undermount sink | 200 | 1 | 200 |  | Jakob | 0 | 0 | [5 empty] | Draw 2 Deposited Date:
kitchen faucet | 129.99 | 1 | 129.99 |  | Justin | 0 | 0 | [5 empty] | Draw 3 Amount:
bathroom faucet | 89.99 | 1 | 89.99 |  | Carey | 0 | 0 | [5 empty] | Draw 3 Deposited Date:
shower & tub faucet | 184.99 | 1 | 184.99 | 126.24 | TOTAL | 0 | 0 | [5 empty] | Draw 4 Amount:
bathroom fixtures | 75 | 1 | 75 |  | Time Sheets | Week of: | [6 empty] | Draw 4 Deposited Date:
tub and surround | 1000 | 1 | 1000 | 491.01 | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | Final Payment Amount:
Sterling Finese Shower Door | 279 | 1 | 279 |  | Tristan | 0 | 0 | [5 empty] | Final Payment Deposited Date:
vanity | 750 | 1 | 750 |  | Jessica | 0 | 0 | [5 empty] | NOTES
mirror | 100 | 1 | 100 |  | Davon | 0 | 0 | [5 empty] | WHAT WENT WELL?
vanity lights | 100 | 1 | 100 |  | Jakob | 0 | 0
toilet | 300 | 1 | 300 |  | Justin | 0 | 0
exhaust fan and venting | 250 | 1 | 250 |  | Carey | 0 | 0
laundry sink | 250 | 1 | 250 | 277.85 | TOTAL | 0 | 0
cabinets white shaker style | 515.62 | 3 | 1546.86 |  | Time Sheets | Week of:
counter top - quartz | 100 | 8 | 800 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
paint | 30 | 14 | 420 |  | Tristan | 0 | 0
Rinnai tankless water heater |  |  |  | 1389.86 | Jessica | 0 | 0
saw and jackhammer rental |  |  |  | 364.34 | Davon | 0 | 0
Permit | 150 | 0 |  | 526 | Jakob | 0 | 0
Total Material Cost |  |  | 9764.12 | 3847.69 | Justin | 0 | 0
Plus Tax |  |  | 10310.9107 | 0 | Carey | 0 | 0
plumber |  |  | 5500 | 4366.3 | TOTAL | 0 | 0
electrician |  |  | 3500 |  | Time Sheets | Week of:
HVAC |  |  | 3000 | 3180 | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Egress Window |  |  | 5000 | 5961 | Tristan | 0 | 0
drywaller |  |  | 9000 |  | Jessica | 0 | 0 | [5 empty] | WHAT DID NOT GO WELL?
painter |  |  | 2000 |  | Davon | 0 | 0
carpet installation |  |  | 900 |  | Jakob | 0 | 0
Dumpster |  |  | 450 | 430 | Justin | 0 | 0
Glass Block Windows |  |  | 0 | 150 | Carey | 0 | 0
Drop Ceiling |  |  | 3000 |  | TOTAL | 0 | 0
concrete |  |  |  | 500 | Time Sheets | Week of:
Photographer |  |  | 100 |  | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
Edible Arrangement |  |  | 100 |  | Tristan | 0 | 0
Back to Basics Employee Labor ($800/day) | 800 | 11 | 8800 |  | Jessica | 0 | 0
Total Labor Costs |  |  | 41350 | 14587.3 | Davon | 0 | 0
Total Variable Costs |  |  | 51660.9107 | 14587.3 | Jakob | 0 | 0
Profit (20%) |  |  | 10332.1821 | 2917.46 | Justin | 0 | 0
Total Estimate |  |  | 61993.0929 | 17504.76 | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0
[5 empty] | Time Sheets | Week of:
[5 empty] | Date: | TOTAL HOURSHours Worked | Cost | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY
[5 empty] | Tristan | 0 | 0
[5 empty] | Jessica | 0 | 0
[5 empty] | Davon | 0 | 0
[5 empty] | Jakob | 0 | 0
[5 empty] | Justin | 0 | 0
[5 empty] | Carey | 0 | 0
[5 empty] | TOTAL | 0 | 0